## Timeline
Week | Date | Task | Team Assignment | Deadline
1 | 2018-02-05 | Project Proposal | All | 2018-02-12
2 | 2018-02-12 | Prototyping - Interface Design | All | 2018-02-19
3 | 2018-02-19 | Prototyping - Application Logic Theory | All | 2018-02-26
4 | 2018-02-26 | Back End Search - Seek out best possible avenues for implementing the back end portion. Start Database setup and backend implementation | All | 2018-03-02
5 | 2018-03-05 | Front End Search - Seek out best possible avenues for implementing front end portion. Start front end development and server setup | All | 2018-03-09
6 | 2018-03-12 | Work on backend API and front end features | All | 2018-03-16
7 | 2018-03-19 | Work on Web Interface / Backend connections | All | 2018-03-23
8 | 2018-03-26 | Finish Web Interface / Finish Back end and Database | All | 2018-03-30
9 | 2018-04-02 | Connect Front end and Back end | All | 2018-04-06
10 | 2018-04-09 | Make adjustments and finish anything that is behind schedule | All | 2018-04-13
11 | 2018-04-16 | QA Testing / Fixing | All | 2018-04-20
12/13 | 2018-04-23 | Prepare Final Submission | All | 2018-05-04

## WorkPlan
Project Piece | Start Date | Finish Date | Lead Developer | Comments | Status
Proposal | 2018-02-01 | 2018-02-13 | All |  | Complete
Prototype | 2018-02-08 |  | All |  | Started
Splash Screen |  |  | Chris |  | Not Started
Login Screen |  |  | Chris |  | Not Started
Sign Up Screen |  |  | Chris |  | Not Started
Ticket View Screen |  |  | Chris |  | Not Started
Basic User Interface |  |  | Chris |  | Not Started
Database Structure |  |  | Ryan |  | Not Started
Database API |  |  | Ryan |  | Not Started
Javascript population of tickets |  |  | Salem |  | Not Started
Login System |  |  | Ryan |  | Not Started
Signup System |  |  | Ryan |  | Not Started
Logout System |  |  | Ryan |  | Not Started
Create New Ticket |  |  | Salem |  | Not Started
Edit Ticket |  |  | Salem |  | Not Started
Remove Ticket |  |  | Salem |  | Not Started
Sort Tickets |  |  | Salem |  | Not Started
Search Tickets |  |  | Salem |  | Not Started
Not Started
Started
Complete